## Worklog_Tasks&Times
Date | Status | Task | Description/Planning | Task Type | Most suited ILO | Est Hours | Actual Hours | Diff | Evidence link | Task reflection / notes
Week 1
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2023-11-20 | Done | Max 4 hours tasks | Set up your IDE for ML | Lecture | ILO 4.2 - Phyton libraries | 1 | 1 | 0
2023-11-20 | Done | Max 4 hours tasks | Unit testing first chapter | Study | ILO 4.2 - Phyton libraries | 4 | 4 | 0
2023-11-20 | Done | Max 4 hours tasks | Learn coding standards | Study | ILO 4.1 - Phyton Api | 1 | 1 | 0
2023-11-21 | Done | Max 4 hours tasks | Stand up with Mentor Group | Meeting | ILO 1.4 - Work log | 0.5 | 0.5 | 0
2023-11-21 | Done | Max 4 hours tasks | Kick-off | Meeting | ILO 1.4 - Work log | 2 | 2 | 0
2023-11-21 | Done | Max 4 hours tasks | reviewng block A | Meeting | ILO 1.4 - Work log | 1 | 1 | 0
2023-11-21 | Done | Max 4 hours tasks | set up your IDE for ML | Programming | ILO 4.1 - Phyton Api | 1 | 1 | 0
2023-11-22 | Done | Max 4 hours tasks | Pandas data camp course | Workshop | ILO 4.2 - Phyton libraries | 4 | 4 | 0
2023-11-22 | Done | Max 4 hours tasks | Football descriptions | Design | ILO 1.4 - Work log | 2 | 2 | 0
2023-11-22 | Done | Max 4 hours tasks | File Formats and Pandas | Study | ILO 4.2 - Phyton libraries | 2 | 2 | 0
2023-11-22 | Done | Max 4 hours tasks | DataCamp Courses on Importing | Workshop | ILO 1.4 - Work log | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24b-fai1-adsai-PetarPaskalev232725/blob/main/Certificates/certificate-%20Introduction%20to%20I%20mporting%20Data%20in%20Phyton.pdf
2023-11-23 | Done | Max 4 hours tasks | Directories and its importance | Study | ILO 4.2 - Phyton libraries | 1 | 1 | 0
2023-11-23 | Done | Max 4 hours tasks | Introduction to NumPy | Study | ILO 4.2 - Phyton libraries | 2 | 2 | 0
2023-11-23 | Done | Max 4 hours tasks | Elementary Matrices operations | Study | ILO 4.1 - Phyton Api | 2 | 2 | 0
2023-11-23 | Done | Max 4 hours tasks | Intro to NumPy Hands-on | Debugging | ILO 4.2 - Phyton libraries | 2 | 2 | 0
2023-11-24 | Done | Max 4 hours tasks | Phyton script on pandas 1 | Programming | ILO 4.1 - Phyton Api | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24b-fai1-adsai-PetarPaskalev232725/blob/main/Deliverables/Week1DataLabII_Python_23725.ipynb | This task was from the first week, specifically on Friday. It was challenging, but it provided me with a better understanding of NumPy arrays and expanded my knowledge of pandas as well.
2023-11-24 | Done | Max 4 hours tasks | Phyton script on pandas 2 | Programming | ILO 4.2 - Phyton libraries | 1.5 | 1.5 | 0
2023-11-24 | Done | Max 4 hours tasks | Phyton script on pandas 3 | Programming | ILO 4.1 - Phyton Api | 1.5 | 1.5 | 0
2023-11-24 | Done | Max 4 hours tasks | Phyton script on pandas 4 | Programming | ILO 4.1 - Phyton Api | 1.5 | 1.5 | 0
2023-11-24 | Done | Max 4 hours tasks | Phyton script on pandas 5 | Programming | ILO 4.2 - Phyton libraries | 1 | 1 | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  |  |  | Total Hours |  | 35 | 35 | 0
Week 2
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning] - if any
2023-11-27 | Done | Max 4 hours tasks | Introduction into ethics | Study | ILO 3.1 - Ethics and law | 2 | 2 | 0
2023-11-27 | Done | Max 4 hours tasks | Ethics and business | Study | ILO 3.1 - Ethics and law | 1 | 1 | 0
2023-11-27 | Done | Max 4 hours tasks | Ai ethics | Evidencing | ILO 3.1 - Ethics and law | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24b-fai1-adsai-PetarPaskalev232725/blob/main/Data_lab%20preparation/The%20ownership%20of%20player.docx
2023-11-27 | Done | Max 4 hours tasks | Catching up on Friday assignment | Programming | ILO 4.2 - Phyton libraries | 1.5 | 1.5 | 0
2023-11-28 | Done | Max 4 hours tasks | Stand up with Mentor Group | Meeting | ILO 1.4 - Work log | 0.5 | 0.5 | 0
2023-11-28 | Done | Max 4 hours tasks | Critical thinking and reasoning | Study | ILO 6.0 - Reporting | 2 | 2 | 0
2023-11-28 | Done | Max 4 hours tasks | Choosing dialogue | Research | ILO 6.0 - Reporting | 0.5 | 0.5 | 0
2023-11-28 | Done | Max 4 hours tasks | Topics of the dialogue | Study | ILO 3.1 - Ethics and law | 2 | 2 | 0
2023-11-28 | Done | Max 4 hours tasks | Starting on my report | Meeting | ILO 6.0 - Reporting | 1 | 1 | 0
2023-11-29 | Done | Max 4 hours tasks | Introduction into professional writing and APA | Study | ILO 6.0 - Reporting | 2 | 2 | 0
2023-11-29 | Done | Max 4 hours tasks | Writing styles | Study | ILO 6.0 - Reporting | 4 | 4 | 0
2023-11-29 | Done | Max 4 hours tasks | Bias-Free-Language | Study | ILO 3.1 - Ethics and law | 1 | 1 | 0
2023-11-29 | Done | Max 4 hours tasks | Creating a folder with all checklist and handouts | Study | ILO 6.0 - Reporting | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24b-fai1-adsai-PetarPaskalev232725/tree/main/Hand-outs_checklists
2023-11-30 | Done | Max 4 hours tasks | Citation | Study | ILO 6.0 - Reporting | 1 | 1 | 0
2023-11-30 | Done | Max 4 hours tasks | Writing report for the dialogue | Study | ILO 6.0 - Reporting | 3 | 3 | 0
2023-11-30 | Done | Max 4 hours tasks | Ethical Guidelines for Statistical Parctise | Study | ILO 3.1 - Ethics and law | 1 | 1 | 0
2023-11-30 | Done | Max 4 hours tasks | GDPR understanding | Study | ILO 6.0 - Reporting | 1 | 1 | 0
2023-11-30 | Done | Max 4 hours tasks | Writing report for the dialogue | Study | ILO 6.0 - Reporting | 2 | 2 | 0
2023-12-01 | Done | Max 4 hours tasks | Stand up with Mentor Group | Meeting | ILO 1.4 - Work log | 0.5 | 0.5 | 0
2023-12-01 | Done | Max 4 hours tasks | Dialogue | Meeting | ILO 3.1 - Ethics and law | 1 | 1 | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  |  |  | Total Hours |  | 29.5 | 29.5 | 0
Week 3
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2023-12-04 | Done | Max 4 hours tasks | Linear Algebra and Linear Systems | Study | ILO 7.0 - Math | 1 | 2 | 1 |  | It was more time than I expected the format of the exercise wasn't fromulated perfectly
2023-12-04 | Done | Max 4 hours tasks | Broadcasting and Vectorising | Study | ILO 7.0 - Math | 2 | 2 | 0
2023-12-04 | Done | Max 4 hours tasks | Datalab Preparation- using numpy to solve equations | Study | ILO 7.0 - Math | 2 | 2 | 0
2023-12-04 | Done | Max 4 hours tasks | Introduction to data visualizations with matplotlib | Study | ILO 4.2 - Phyton libraries | 1 | 1 | 0
2023-12-04 | Done | Max 4 hours tasks | Plotting 5 random images | Study | ILO 4.2 - Phyton libraries | 2 | 2 | 0
2023-12-05 | Done | Max 4 hours tasks | Stand up with Mentor Group | Meeting | ILO 1.4 - Work log | 0.5 | 0.5 | 0
2023-12-05 | Done | Max 4 hours tasks | Making the whole data set | Programming | ILO 4.2 - Phyton libraries | 2.5 | 1.5 | -1 | https://github.com/BredaUniversityADSAI/2023-24b-fai1-adsai-PetarPaskalev232725/blob/main/Deliverables/NAC_project/DataLab_I_Week3_NAC_Preprocessing_1.ipynb.ipynb | We were doing a job together with one of my colleagues and that is why it didn't took me that much time
2023-12-05 | Done | Max 4 hours tasks | Finding numerical and categorigal variables | Programming | ILO 4.2 - Phyton libraries | 2 | 2 | 0
2023-12-05 | Done | Max 4 hours tasks | Finding market value of the players | Programming | ILO 4.2 - Phyton libraries | 2 | 2 | 0
2023-12-05 | Done | Max 4 hours tasks | 1 | Programming | ILO 4.2 - Phyton libraries | 1 | 1 | 0
2023-12-06 | Done | Max 4 hours tasks | Learning about API | Study | ILO 4.1 - Phyton Api | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24b-fai1-adsai-PetarPaskalev232725/blob/main/Data_lab%20preparation/Week3DataPrep2_232725_API.ipynb.ipynb
2023-12-06 | Done | Max 4 hours tasks | Writing API | Study | ILO 4.1 - Phyton Api | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24b-fai1-adsai-PetarPaskalev232725/blob/main/Data_lab%20preparation/Week3DataPrep2_232725_API.ipynb.ipynb
2023-12-06 | Done | Max 4 hours tasks | Data Visualization - NAC Data 5 images from Tuesday | Study | ILO 4.2 - Phyton libraries | 3 | 3 | 0 |  | Need a better calrification what to story to be need to look back further on it
2023-12-07 | Done | Max 4 hours tasks | Introduction to streamlit | Programming | ILO 4.2 - Phyton libraries | 3 | 3 | 0
2023-12-07 | Done | Max 4 hours tasks | Create a simple calculator streamlit app | Programming | ILO 4.2 - Phyton libraries | 2 | 2 | 0
2023-12-07 | Done | Max 4 hours tasks | Basics of Python | Programming | ILO 4.2 - Phyton libraries | 2 | 2 | 0
2023-12-08 | Done | Max 4 hours tasks | Data Analysis qestion 1 to 10 | Programming | ILO 4.2 - Phyton libraries | 3 | 4 | 1
2023-12-08 | Done | Max 4 hours tasks | Data Analysis question 11 to 20 | Programming | ILO 4.2 - Phyton libraries | 3 | 4 | 1
2023-12-08 | Done | Max 4 hours tasks | Data Analysis making a a spliter for positons | Programming | ILO 4.2 - Phyton libraries | 2 | 4 | 2 |  | We have been working on this problem for a while because it did not make sense in the dataset to be this way, so we needed to find a better solution.
|  |  |  | Total Hours |  | 38 | 42 | 4
Week 4
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2023-12-11 | Done | Max 4 hours tasks | Introduction to Machine Learning | Study | ILO 5.1 - ML | 1 | 1 | 0
2023-12-11 | Done | Max 4 hours tasks | Machine leraning Data Camp course | Study | ILO 5.1 - ML | 3 | 3 | 0
2023-12-11 | Done | Max 4 hours tasks | Feature Engineering | Study | ILO 5.1 - ML | 3 | 1 | -2 | https://github.com/BredaUniversityADSAI/2023-24b-fai1-adsai-PetarPaskalev232725/blob/main/Deliverables/NAC_project/Week4DataLabPrep_1_FeatureEngg_LRbasics_232725.ipynb | The task provided wasn't clear enough
2023-12-11 | Done | Max 4 hours tasks | Tenets of Linear Regression | Study | ILO 7.0 - Math | 1 | 1 | 0
2023-12-12 | Done | Max 4 hours tasks | Stand up with Mentor Group | Meeting | ILO 1.4 - Work log | 0.5 | 0.5 | 0
2023-12-12 | Done | Max 4 hours tasks | Introduction to Linear Regression | Study | ILO 7.0 - Math | 1 | 1 | 0
2023-12-12 | Done | Max 4 hours tasks | Linear Regression Housing Price Prediction Implemantation | Study | ILO 5.1 - ML | 2 | 3 | 1
2023-12-12 | Done | Max 4 hours tasks | Linear Regression NAC player data | Programming | ILO 7.0 - Math | 3 | 4 | 1
2023-12-12 | Done | Max 4 hours tasks | Visit Nac Breda Stadium | Meeting | ILO 6.0 - Reporting | 2 | 2 | 0
2023-12-13 | Done | Max 4 hours tasks | Logistic Regression Video Tutorials | Study | ILO 7.0 - Math | 4 | 4 | 0
2023-12-13 | Done | Max 4 hours tasks | Guided Walkthrough of Logistic Regression | Study | ILO 7.0 - Math | 1 | 1 | 0
2023-12-13 | Done | Max 4 hours tasks | Linear Regression Backlog | Study | ILO 7.0 - Math | 2 | 3 | 1
2023-12-14 | Done | Max 4 hours tasks | Evaluating Logistic Regression | Study | ILO 7.0 - Math | 2.5 | 2.5 | 0
2023-12-14 | Done | Max 4 hours tasks | k Nearest Neighbours Algorithm | Study | ILO 7.0 - Math | 3 | 3 | 0
2023-12-14 | Done | Max 4 hours tasks | Comparison | Study | ILO 5.1 - ML | 1 | 1 | 0
2023-12-15 | Done | Max 4 hours tasks | Stand up meeting | Meeting | ILO 1.4 - Work log | 0.25 | 0.25 | 0
2023-12-15 | Done | Max 4 hours tasks | Nac player calsiffication binning | Study | ILO 5.1 - ML | 2 | 2 | 0 |  | The process of binning was quite easy.
2023-12-15 | Done | Max 4 hours tasks | Nac player calsiffication Logistic regression | Study | ILO 5.1 - ML | 3 | 3 | 0 |  | Had to make a ceparate cell for the kn mean
2023-12-15 | Done | Max 4 hours tasks | Nac player calsiffication knn mean | Study | ILO 5.1 - ML | 1 | 1 | 0
Max 4 hours tasks
|  |  |  | Total Hours |  | 36.25 | 37.25 | 1
Week 5
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2023-12-18 | Done | Max 4 hours tasks | Cross-Validation | Study | ILO 5.1 - ML | 5 | 5 | 0 | https://github.com/BredaUniversityADSAI/2023-24b-fai1-adsai-PetarPaskalev232725/blob/main/Data_lab%20preparation/Week5DataLabPrep_1_clusteringandcrossvalid_studentid.ipynb
2023-12-18 | Done | Max 4 hours tasks | Introduction to Clustering | Study | ILO 5.1 - ML | 3 | 3 | 0
2023-12-19 | Done | Max 4 hours tasks | Stand up meeting | Study | ILO 1.4 - Work log | 0.25 | 0.25 | 0
2023-12-19 | Done | Max 4 hours tasks | Clustering Hands-on | Study | ILO 5.1 - ML | 6 | 6 | 0
2023-12-19 | Done | Max 4 hours tasks | Ibm Presentation | Lecture | ILO 5.1 - ML | 2 | 2 | 0
2023-12-20 | Done | Max 4 hours tasks | Introduction to Decision trees | Study | ILO 5.1 - ML | 4 | 4 | 0
2023-12-20 | Done | Max 4 hours tasks | DataCamp course - Decision Trees | Study | ILO 5.1 - ML | 3 | 3 | 0
2023-12-20 | Done | Max 4 hours tasks | Hands-on Decision Trees | Study | ILO 5.1 - ML | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2023-24b-fai1-adsai-PetarPaskalev232725/blob/main/Data_lab%20preparation/Week5DataLabPrep_2_scikit_learn_studentid.ipynb
|  |  |  | Total Hours |  | 24.25 | 24.25 | 0
Week 6
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2024-01-08 | Done | Max 4 hours tasks | Data Camp course - decision trees | Study | ILO 5.1 - ML | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24b-fai1-adsai-PetarPaskalev232725/blob/main/Certificates/certificate-Mchine%20Learning%20with%20Tree-%20Based%20Models%20in%20Phyton.pdf
2024-01-08 | Done | Max 4 hours tasks | Random Forests- Introduction | Study | ILO 5.1 - ML | 4 | 4 | 0 | https://github.com/BredaUniversityADSAI/2023-24b-fai1-adsai-PetarPaskalev232725/blob/main/Data_lab%20preparation/Week6DataLabPrep_1_scikit_learn_232725.ipynb
2024-01-08 | Done | Max 4 hours tasks | Final Deliverable Notebook Template (clustering | Study | ILO 5.1 - ML | 2 | 2 | 0
2024-01-09 | Done | Max 4 hours tasks | Stand up datalab sesion | Meeting | ILO 1.4 - Work log | 0.25 | 0.25 | 0
2024-01-09 | Done | Max 4 hours tasks | Review sesion | Meeting | ILO 1.4 - Work log | 1 | 1 | 0
2024-01-09 | Done | Max 4 hours tasks | Application on NAC Dataset- Random forest | Programming | ILO 5.1 - ML | 5.5 | 5.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24b-fai1-adsai-PetarPaskalev232725/blob/main/Deliverables/NAC_project/Week6DataLab1_RandomForests_232725.ipynb
2024-01-09 | Done | Max 4 hours tasks | NAC Q&A with Paul from Nac | Lecture | ILO 1.4 - Work log | 1 | 2 | 1 |  | Understood I lot of concept of what we should do with the project itself
2024-01-10 | Done | Max 4 hours tasks | Bagging and Boosting | Study | ILO 4.2 - Phyton libraries | 2.5 | 2.5 | 0
2024-01-10 | Done | Max 4 hours tasks | DataCamp Course - gradient boosting | Study | ILO 5.1 - ML | 2 | 2 | 0
2024-01-10 | Done | Max 4 hours tasks | Gradient Boosting Algorithm Hands-on | Study | ILO 5.1 - ML | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24b-fai1-adsai-PetarPaskalev232725/blob/main/Data_lab%20preparation/Week6DataLabPrep_1_XGB_232725.ipynb
2024-01-11 | Done | Max 4 hours tasks | Introduction to Hyperparameters | Study | ILO 5.1 - ML | 2.5 |  | -2.5
2024-01-11 | Done | Max 4 hours tasks | DataCamp course - Hyperparameters | Study | ILO 4.1 - Phyton Api | 2 |  | -2
2024-01-11 | Done | Max 4 hours tasks | Hands-on Hyperparameter Tuning | Study | ILO 4.2 - Phyton libraries | 2.5 |  | -2.5
2024-01-12 | Planned | Max 4 hours tasks | Stand up datalab sesion | Meeting | ILO 1.4 - Work log | 1 |  | -1
2024-01-12 | Planned | Max 4 hours tasks | Consolidating ML Algorithms for NAC Dataset | Programming | ILO 4.1 - Phyton Api | 5.5 |  | -5.5
Max 4 hours tasks
|  | Max 4 hours tasks | [5 empty] | 0
|  |  |  | Total Hours |  | 35.75 | 23.25 | -12.5
Week 7
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2024-01-15 | Done | Max 4 hours tasks | Principal Component Analysis and Dimensionality Reduction | Study | ILO 7.0 - Math | 4 | 4 | 0
2024-01-15 | Done | Max 4 hours tasks | Data camp course - Dimensionality Reduction | Study | ILO 7.0 - Math | 5 | 5 | 0
2024-01-16 | Done | Max 4 hours tasks | Review | Meeting | ILO 4.2 - Phyton libraries | 0.5 | 0.5 | 0
2024-01-16 | Done | Max 4 hours tasks | Improving Performance metrics | Study | ILO 4.1 - Phyton Api | 2 | 2 | 0
2024-01-16 | Done | Max 4 hours tasks | Hands-on Final model | Programming | ILO 4.1 - Phyton Api | 4 | 4 | 0
2024-01-17 | Done | Max 4 hours tasks | Videos on Exploring Calculus: Derivatives, Limits, and Applications | Study | ILO 7.0 - Math | 1 | 1 | 0
2024-01-17 | Cancelled | Max 4 hours tasks | Khan- Differential Calculus unit 1 | Study | ILO 7.0 - Math | 5 |  | -5
2024-01-17 | Cancelled | Max 4 hours tasks | Khan- Differential Calculus unit 2 | Study | ILO 7.0 - Math | 4 |  | -4
2024-01-18 | Cancelled | Max 4 hours tasks | Videos on Multivariable Calculus | Study | ILO 7.0 - Math | 0.5 |  | -0.5
2024-01-18 | Cancelled | Max 4 hours tasks | Assignment Compute all partial derivatives 1 | Study | ILO 7.0 - Math | 3 |  | -3
2024-01-18 | Cancelled | Max 4 hours tasks | Assignment Compute all partial derivatives 1 | Study | ILO 7.0 - Math | 3 |  | -3
2024-01-19 | Done | Max 4 hours tasks | Stand up datalab sesion | Study | ILO 1.4 - Work log | 0.5 |  | -0.5
2024-01-19 | Done | Max 4 hours tasks | Filling my worklog | Evidencing | ILO 1.4 - Work log | 2 | 2 | 0
2024-01-19 | Done | Max 4 hours tasks | Filling my Learning Log | Evidencing | ILO 2.5 - Learning Log | 1 | 1 | 0
2024-01-19 | Done | Max 4 hours tasks | Working on my project | Programming | ILO 4.2 - Phyton libraries | 10 | 10 |  |  | I did this during the weekend
|  |  |  | Total Hours |  | 45.5 | 29.5 | -16
Week 8
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2024-01-22 | Done | Max 4 hours tasks | Working on project handle missing values | Programming | ILO 4.1 - Phyton Api | 3 | 3 | 0
2024-01-22 | Done | Max 4 hours tasks | Working clustering | Programming | ILO 4.2 - Phyton libraries | 4 | 4 | 0
2024-01-22 | Done | Max 4 hours tasks | Filling section C Ilos Learning log | Evidencing | ILO 2.5 - Learning Log | 4 | 4 | 0
2024-01-23 | Done | Max 4 hours tasks | Report section Introduction | Programming | ILO 6.0 - Reporting | 3 | 3 | 0
2024-01-23 | Done | Max 4 hours tasks | Report section EDA part one | Programming | ILO 6.0 - Reporting | 4 | 4 | 0
2024-01-24 | Done | Max 4 hours tasks | Report section EDA part two | Programming | ILO 6.0 - Reporting | 4 | 4 | 0
2024-01-24 | Done | Max 4 hours tasks | Project machine learning | Debugging | ILO 5.1 - ML | 7 | 7 | 0 |  | I had a lot of problems with the debugging
2024-01-24 | Done | Max 4 hours tasks | Report section machine learning | Debugging | ILO 6.0 - Reporting | 5 | 5 | 0
2024-01-25 | Done | Max 4 hours tasks | Report section data goveranace | Debugging | ILO 6.0 - Reporting | 4 | 4 | 0
2024-01-26 | Done | Max 4 hours tasks | Report section on reccomendention | Debugging | ILO 6.0 - Reporting | 4 | 4 | 0
2024-01-26 | Done | Max 4 hours tasks | Filling all the missing points | Evidencing | ILO 1.4 - Work log | 4 | 4 | 0
2024-01-26 | Done | Max 4 hours tasks | Finishing on the project | Programming | ILO 4.2 - Phyton libraries | 5 | 5 | 0
2024-01-26 | Done | Max 4 hours tasks | Filling all the code in the final deliverable | Programming | ILO 4.1 - Phyton Api | 5 | 5 | 0
|  |  |  | Total Hours |  | 56 | 56 | 0
|  |  |  | Total hours this block |  | 300.25 | 276.75 | -23.5

## Overview
Learning Objective | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | Total Hours for objective
- | [8 empty] | 0
ILO 1.4 - Work log | W1: 0 | 0
ILO 2.5 - Learning Log | [8 empty] | 0
ILO 3.1 - Ethics and law | [8 empty] | 0
ILO 4.1 - Phyton Api | [8 empty] | 0
ILO 4.2 - Phyton libraries | [8 empty] | 0
ILO 5.1 - ML | [8 empty] | 0
ILO 6.0 - Reporting | [8 empty] | 0
ILO 7.0 - Math | [8 empty] | 0
TOTAL HOURS PER WEEK | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Use this to plan a high level allocation for all 320 hours you are expected to devote to the course during this block. How do you want to allocate your hours for each week? Why 320 hours? The European Higher Education Framework states that an academic credit is expected to require 25-28 hours to earn. You earn 15 credits per block, so you should be expected to devote 375 hours to accomplish that. CMGT students do fewer hours because the program is more intense.
Use a formula like this to get your data from Worklog sheet : =IFERROR(SUM(FILTER('Worklog_Tasks&Times'!$H$5:$H$14,'Worklog_Tasks&Times'!$F$5:$F$14=$B4)),0)

## Drop-downs
Task Status | Task Type | ILO selection
- | - | -
Planned | Design | ILO 1.4 - Work log
Unplanned | Meeting | ILO 2.5 - Learning Log
Blocked | Programming | ILO 3.1 - Ethics and law
In-Progress | Research | ILO 4.1 - Phyton Api
Done | Testing | ILO 4.2 - Phyton libraries
Delayed | Workshop | ILO 5.1 - ML
Cancelled | Planning | ILO 6.0 - Reporting
| Evidencing | ILO 7.0 - Math
Debugging
Lecture
Study
Unplanned
Distraction
Break